## Sheet1
Test Case ID | Objective | Test Scenario | test resources | Expected result | Actual result | status
TC_v_01 | to check that 12 hours system is working proberly | Run clock for 24 hours and compare the results with the results of an external clock | hardware resource: the complete hardware circuit, oscillscope for measuring the clock width | the results are the same |  | PENDING
TC_v_02 | to check that Stop watch is working as mentioned in CRS | Run the system at stop watch mode ,after few seconds pause the clock by pressing middle switch ,press middle switch again for less than 3 seconds ,pause stop watch again then press middle switch more than 3 seconds,calibrate time of pressing switch using external stop watch | human recorses: all team memebrs | the customer should get ascending stop watch ,if it is paused then resume button is pressed for less than 3 seconds ,stop watch will continue working but if resume switch is pressed for mor than 3 seconds ,stop watch will reset | result was as expected | PASSEd
TC_v_03 | to check the time is being edited in the same way the customer mentioned | switch between hours,seconds,minutes,AM/PM using mode switch,press increment or decrement switch for less than 3 seconds then press again for more than 3 seconds | Software resources: application code | switch between hours,seconds,minutes,AM/PM using mode switch.for example if mode switch was pressed for 1 time and increment switch is pressed for less than 3 seconds minutes will be incremented by 1 but if switch is pressed for more than 3 seconds minutes will keep incrementing till switch is released | Actual result was as expected | PASSED
TC_v_04 | System Start at clock mode | Run the system |  | Clock is working and time is being updated at LCD | Clock is working and time is being updated at LCD | PASSED
TC_V_05 | test the case of pressing muliple switches at the same time | Run the System |  | differs from time to time depending on the speed of pressing | differs from time to time depending on the speed of pressing | PASSED