## Sheet1
Review No. | Document Name | Changes | date reviewed | Complexity | assigned person | Status | Reviewed by
rev-01 | SRS | SRS is not linked proberly with the CRS. The last requirement in the CRS got no SRS | 18/3/2016 | Easy | Ahmed Adel | DONE | anwar abd elhamid
rev-02 | CRS | needs to be updated with the ISQ sheet | 18/3/2016 | Easy | Norhan osama | DONE | anwar abd elhamid
rev-03 | Project Schedule | needs to be updated with the finished tasks, HLD, CDD, APP design and hardware design | 28/3/2016 | Hard | Seif eldin | PENDING | anwar abd elhamid
rev-03 | Project plane
rev-04 | DIO_CDD | re organize the sections of the document, | 28/3/2016 | Med | Walaa | DONE | Seif eldin
rev-05 | HLD | add the the Timer module to the Mcal layer | 30/3/2016 | Med | anwar | DONE | Seif eldin
rev-06 | LCD_CDD | fixing some gramatical mistakes. Adding the dependant modules. | 2016-01-04 | Med | Norhan osama | DONE | Seif eldin
rev-07 | LCD_CDD | adding config macros | 2016-01-04 | Easy | Seif eldin | DONE | Seif eldin
rev-08 | DIO_CDD | adding macros | 2016-01-04 | Easy | walaa | DONE | Seif eldin
rev-09 | DIO_TEST | more test scenarios needed for each funtion | 2016-07-04 | Med | abdel azim | DONE | Seif eldin
rev-10 | DIO_TEST | testcases column needs to be renamed to function ID. | 2016-08-04 | Easy | abdel azim | PENDING | Seif eldin
rev-11 | SWITCH_TEST | test scnearios are too few ,more unhappy scenarios needed | 2016-08-04 | Easy | anwar | PENDING | seif eldin